## Sheet1
REQUIREMENTS TRACEABILITY MATRIX
COMS3-MISIS
Business Requirement ID | Business Requirement | Business Requirements Requestor | Functional Requirement ID | Functional Requirement / Use Case | Test Strategy | Execution Status | Comments
BR_1 | Login module | Richard Klein | FR_1 | Allow admin user access | Load and functionality user testing | pass
|  |  | FR_2 | Allow standard user access | Load and functionality user testing | pass
|  |  | FR_3 | Deny access to unauthoized users | Load and functionality user testing | pass
BR_2 | View Module | Richard Klein | FR_4 | List users | Load and functionality user testing | pass
|  |  | FR_5 | Filter users by course | Load and functionality user testing | pass
|  |  | FR_6 | Search for specific users | Load and functionality user testing | pass
|  |  | FR_7 | Add new user | Load and functionality user testing | pass
|  |  | FR_8 | Edit selected user | Load and functionality user testing | fail | Button not functional
|  |  | FR_9 | Delete selected user | Load and functionality user testing | pass
BR_3 | View Details Module | Richard Klein | FR_10 | View details for selected user | Load and functionality user testing | pass
BR_4 | Edit Details Module | Richard Klein | FR_11 | Edit details for selected user | Load and functionality user testing | fail | not yet implemented
BR_5 | Retreive Data Module | Richard Klein | FR_12 | Obtain data from Wits Virtus system and parse JSON to database | Load and functionality user testing | pending | insufficient access to system